## ReadMe
This sheet summarizes what kind of complexity do the example sheets of projects, tasks, and teams have
Sheet | Complexity
Projects | Group
Tasks | Dependencies
Teams | Simple

## Projects
ProjectID | Project Name | Project Group Id | Team Id
1 | Project A | 1 | 1
2 | Project B | 1 | 1
3 | Project C | 2 | 1
4 | Project D | 2 | 1

## Tasks
ID | Project Id | ProjectName | TaskName | EstimatedEffortHours | Dependencies | Progress | InternalID
1 | 1 | Project A | Design UI | 100 |  | 50 | 1234
2 | 1 | Project A | Implement Backend | 55 | 1 |  | 1235
3 | 1 | Project A | Testing | 15 | 2 |  | 123
4 | 2 | Project B | Database Setup | 60 |  |  | 1327
5 | 2 | Project B | API Development | 50 | 4 |  | 1236
6 | 3 | Project C | Database Setup | 30 |  |  | 35413
7 | 3 | Project C | UI Development | 56 |  |  | 4654
8 | 4 | Project D | Backend Analysis | 47 |  |  | 3135
9 | 4 | Project D | Database Setup | 75 |  |  | 1314
10 | 4 | Project D | Implement Backend | 45 |  |  | 13486
11 | 4 | Project D | UI Development | 46 |  |  | 1314
12 | 4 | Project D | Testing | 47 |  |  | 13486

## Teams
Team ID | Team Name | Developer Id | Developer Name | Developer Vacation Date Intervals | Daily Work Hours
1 | Team Alpha | 1 | Alice | 2026-08-10;2026-08-15¦2026-05-10;2026-05-15¦ | 6
1 | Team Alpha | 2 | Bob |  | 7
1 | Team Alpha | 3 | Charlie | 2026-06-05;2026-06-10¦ | 7
1 | Team Alpha | 4 | Dave | 2026-07-25;2026-07-28¦ | 6